## Release Date
Release Date | 2026-12-10

## b18_schedule_prep_spreadsheet
Title | Repo | Start Date | End Date | Length (days) | Completion Days Before Release | Description | Checklist | GitHub Project Product | Validate Start Date | Validate End Date
$BUILD Release Planning | NASA-PDS/software-issues-repo | 2026-03-13 | 2026-04-23 | 41 | 231 | LOE support for high priority improvements to Validate |  | System Engineering | TRUE | TRUE
$BUILD Registry Legacy Support: High Priority Enhancements / Bug Fixes / Tasks | NASA-PDS/registry-legacy-solr | 2026-04-03 | 2026-09-17 | 167 | 84 | LOE support for high priority improvements to Legacy Solr Registry |  | System Engineering
$BUILD Validate Support: High Priority Enhancements / Bug Fixes / Tasks | NASA-PDS/validate | 2026-04-03 | 2026-09-17 | 167 | 84 | LOE support for high priority improvements to Validate |  | Validate | TRUE | TRUE
$BUILD Registry API Support: High Priority Enhancements / Bug Fixes / Tasks | NASA-PDS/registry-api | 2026-04-03 | 2026-09-17 | 167 | 84 | LOE support for high priority improvements to Registry API |  | Search API | TRUE | TRUE
$BUILD DUM Support: High Priority Enhancements / Bug Fixes / Tasks | NASA-PDS/data-upload-manager | 2026-04-03 | 2026-09-17 | 167 | 84 | LOE support for high priority improvements to Data Upload Manager |  | Data Upload Manager | TRUE | TRUE
$BUILD Registry Support: High Priority Enhancements / Bug Fixes / Tasks | NASA-PDS/registry | 2026-04-03 | 2026-09-17 | 167 | 84 | LOE support for high priority improvements to Registry |  | Registry Tools | TRUE | TRUE
$BUILD Information Model SCR Implementation and LDDTool Updates | NASA-PDS/pds4-information-model | 2026-04-03 | 2026-10-08 | 188 | 63 | Information Model SCR Implementation and LDDTool Updates |  | PDS4 Information Model | TRUE | TRUE
$BUILD SCR Freeze | NASA-PDS/pds4-information-model | 2026-09-17 | 2026-09-17 | 0 | 84 | DDWG SCR Freeze |  | PDS4 Information Model | FALSE | TRUE
$BUILD Triage Security Code Scans | NASA-PDS/software-issues-repo | 2026-09-18 | 2026-10-08 | 20 | 63 | Triage Security Code Scans from SonarCloud | Triage results on SonarCube Cloud;Inform SEO Security that Dispositions are available | System Engineering | TRUE | TRUE
$BUILD Bi-annual Cloud Resource Housekeeping | NASA-PDS/planetary-data-cloud | 2026-09-18 | 2026-10-08 | 20 | 63 | Review cloud resources for possible cost cutting opportunities. See wiki "Bi-Annual Cloud Resource Review" for more details. |  | Cloud Operations
$BUILD Information Model Delivery to I&T | NASA-PDS/pds4-information-model | 2026-09-18 | 2026-10-08 | 20 | 63 | Information Model Delivery to I&T | Wrap up remaining SCR implementations;Deliver IM to I&T | PDS4 Information Model | TRUE | TRUE
$BUILD Standards Documents Updates | NASA-PDS/pds4-information-model | 2026-09-18 | 2026-10-08 | 20 | 63 | Standards Documents Updates | Standards Reference Document Update;Generate labels and DOIs for documents Data Provider's Handbook Updates | PDS4 Information Model | TRUE | TRUE
$BUILD dLDD Integration & Test | NASA-PDS/system-i-n-t | 2026-10-09 | 2026-11-19 | 41 | 21 | Discipline LDD Integration & Test | Generate and Deliver Discipline LDDs for I&T;Discipline LDD Review (dLDD Stewards Teams);Discipline LDD Freeze | I&T and Release | TRUE | TRUE
$BUILD Standards Document Review | NASA-PDS/system-i-n-t | 2026-10-09 | 2026-11-19 | 41 | 21 | Standards Document Review | Review Standards Reference Document Updates;Complete Doc Updates Per Review Comments | I&T and Release | TRUE | TRUE
$BUILD System Integration & Test | NASA-PDS/system-i-n-t | 2026-10-09 | 2026-11-19 | 41 | 21 | System Integration & Test | Perform System Testing;Generate Test Report;Update EN Node webpage with Test Report | I&T and Release | TRUE | TRUE
$BUILD Information Model I&T | NASA-PDS/system-i-n-t | 2026-10-09 | 2026-10-30 | 21 | 41 | Information Model I&T |  | I&T and Release | TRUE | FALSE
$BUILD Delivery & Deployment Review (DDR) | NASA-PDS/system-i-n-t | 2026-10-30 | 2026-12-10 | 41 | 0 | Delivery & Deployment Review (DDR) | Generate and Release Final Release Description Document (RDD);Generate & Submit DDR Presentation;Release Test Report;DDR - TBD date | I&T and Release | TRUE | TRUE
$BUILD Deployment and Release | NASA-PDS/system-i-n-t | 2026-11-20 | 2026-12-10 | 20 | 0 | Deployment and Release | Deployment of Test Environment;Deployment of Production Environment - https://docs.google.com/spreadsheets/d/1f1zK9hdR3RWQP9PiR80EMFQ3xDqca1tK2a7oqSCKuHE/edit?usp=sharing;Webpage Updated - documents , discipline LDDs, TBD mission LDDs;Release announcement to public | I&T and Release | TRUE | TRUE
Formulas:
Start Date = [End Date]-[Length (days)]
End Date = 'Release Date'!$B1-[Completion Days Before Release]
Validate Start Date = IF([Start Date]="","",(MOD(DAYS('Release Date'!$B1,([Start Date]+20)),21)=0))
Validate End Date = IF([End Date]="","",(MOD(DAYS('Release Date'!$B1,[End Date]),21)=0))

## b17_schedule_prep_spreadsheet
Title | Repo | Start Date | End Date | Length (days) | Completion Days Before Release | Description | Checklist | GitHub Project Product | Validate Start Date | Validate End Date
$BUILD Release Planning | NASA-PDS/software-issues-repo | 2026-03-13 | 2026-04-23 | 41 | 231 | LOE support for high priority improvements to Validate |  | System Engineering | TRUE | TRUE
$BUILD Registry Legacy Support: High Priority Enhancements / Bug Fixes / Tasks | NASA-PDS/registry-legacy-solr | 2026-04-03 | 2026-09-17 | 167 | 84 | LOE support for high priority improvements to Legacy Solr Registry |  | System Engineering
$BUILD Validate Support: High Priority Enhancements / Bug Fixes / Tasks | NASA-PDS/validate | 2026-04-03 | 2026-09-17 | 167 | 84 | LOE support for high priority improvements to Validate |  | Validate | TRUE | TRUE
$BUILD Registry API Support: High Priority Enhancements / Bug Fixes / Tasks | NASA-PDS/registry-api | 2026-04-03 | 2026-09-17 | 167 | 84 | LOE support for high priority improvements to Registry API |  | Search API | TRUE | TRUE
$BUILD DUM Support: High Priority Enhancements / Bug Fixes / Tasks | NASA-PDS/data-upload-manager | 2026-04-03 | 2026-09-17 | 167 | 84 | LOE support for high priority improvements to Data Upload Manager |  | Data Upload Manager | TRUE | TRUE
$BUILD Registry Support: High Priority Enhancements / Bug Fixes / Tasks | NASA-PDS/registry | 2026-04-03 | 2026-09-17 | 167 | 84 | LOE support for high priority improvements to Registry |  | Registry Tools | TRUE | TRUE
$BUILD Information Model SCR Implementation and LDDTool Updates | NASA-PDS/pds4-information-model | 2026-04-03 | 2026-10-08 | 188 | 63 | Information Model SCR Implementation and LDDTool Updates |  | PDS4 Information Model | TRUE | TRUE
$BUILD SCR Freeze | NASA-PDS/pds4-information-model | 2026-09-17 | 2026-09-17 | 0 | 84 | DDWG SCR Freeze |  | PDS4 Information Model | FALSE | TRUE
$BUILD Triage Security Code Scans | NASA-PDS/software-issues-repo | 2026-09-18 | 2026-10-08 | 20 | 63 | Triage Security Code Scans from SonarCloud | Triage results on SonarCube Cloud;Inform SEO Security that Dispositions are available | System Engineering | TRUE | TRUE
$BUILD Bi-annual Cloud Resource Housekeeping | NASA-PDS/planetary-data-cloud | 2026-09-18 | 2026-10-08 | 20 | 63 | Review cloud resources for possible cost cutting opportunities. See wiki "Bi-Annual Cloud Resource Review" for more details. |  | Cloud Operations
$BUILD Information Model Delivery to I&T | NASA-PDS/pds4-information-model | 2026-09-18 | 2026-10-08 | 20 | 63 | Information Model Delivery to I&T | Wrap up remaining SCR implementations;Deliver IM to I&T | PDS4 Information Model | TRUE | TRUE
$BUILD Standards Documents Updates | NASA-PDS/pds4-information-model | 2026-09-18 | 2026-10-08 | 20 | 63 | Standards Documents Updates | Standards Reference Document Update;Generate labels and DOIs for documents Data Provider's Handbook Updates | PDS4 Information Model | TRUE | TRUE
$BUILD dLDD Integration & Test | NASA-PDS/system-i-n-t | 2026-10-09 | 2026-11-19 | 41 | 21 | Discipline LDD Integration & Test | Generate and Deliver Discipline LDDs for I&T;Discipline LDD Review (dLDD Stewards Teams);Discipline LDD Freeze | I&T and Release | TRUE | TRUE
$BUILD Standards Document Review | NASA-PDS/system-i-n-t | 2026-10-09 | 2026-11-19 | 41 | 21 | Standards Document Review | Review Standards Reference Document Updates;Complete Doc Updates Per Review Comments | I&T and Release | TRUE | TRUE
$BUILD System Integration & Test | NASA-PDS/system-i-n-t | 2026-10-09 | 2026-11-19 | 41 | 21 | System Integration & Test | Perform System Testing;Generate Test Report;Update EN Node webpage with Test Report | I&T and Release | TRUE | TRUE
$BUILD Information Model I&T | NASA-PDS/system-i-n-t | 2026-10-09 | 2026-10-30 | 21 | 41 | Information Model I&T |  | I&T and Release | TRUE | FALSE
$BUILD Delivery & Deployment Review (DDR) | NASA-PDS/system-i-n-t | 2026-10-30 | 2026-12-10 | 41 | 0 | Delivery & Deployment Review (DDR) | Generate and Release Final Release Description Document (RDD);Generate & Submit DDR Presentation;Release Test Report;DDR - TBD date | I&T and Release | TRUE | TRUE
$BUILD Deployment and Release | NASA-PDS/system-i-n-t | 2026-11-20 | 2026-12-10 | 20 | 0 | Deployment and Release | Deployment of Test Environment;Deployment of Production Environment - https://docs.google.com/spreadsheets/d/1f1zK9hdR3RWQP9PiR80EMFQ3xDqca1tK2a7oqSCKuHE/edit?usp=sharing;Webpage Updated - documents , discipline LDDs, TBD mission LDDs;Release announcement to public | I&T and Release | TRUE | TRUE
Formulas:
Start Date = [End Date]-[Length (days)]
End Date = 'Release Date'!$B1-[Completion Days Before Release]
Validate Start Date = IF([Start Date]="","",(MOD(DAYS('Release Date'!$B1,([Start Date]+20)),21)=0))
Validate End Date = IF([End Date]="","",(MOD(DAYS('Release Date'!$B1,[End Date]),21)=0))

## Baseline
Task | Repo | Start Date | End Date | Length (days) | End Date - Days from Release | Description | Checklist
Release Planning | NASA-PDS/software-issues-repo | 2025-03-21 | 2025-05-01 | 41 | 588
Security Scan | NASA-PDS/pds4-information-model | 2025-09-26 | 2025-10-16 | 20 | 420
B16 Information Model SCR Implementation and LDDTool Updates | NASA-PDS/pds4-information-model | 2025-04-10 | 2025-10-16 | 189 | 420
B16 SCR Freeze | NASA-PDS/pds4-information-model | 2025-09-26 | 2025-09-26 | 0 | 440 | DDWG SCR Freeze
B16 Information Model Delivery to I&T | NASA-PDS/pds4-information-model | 2025-09-26 | 2025-10-16 | 20 | 420 | Information Model Delivery to I&T | Wrap up remaining SCR implementations;Deliver IM to I&T
B16 Standards Documents Updates | NASA-PDS/pds4-information-model | 2025-09-26 | 2025-10-16 | 20 | 420 |  | Standards Reference Document Update;Generate labels and DOIs for documents Data Provider's Handbook Updates
B16 dLDD Integration & Test | NASA-PDS/system-i-n-t | 2025-10-17 | 2025-11-27 | 41 | 378 | Discipline LDD Integration & Test | Generate and Deliver Discipline LDDs for I&T;Discipline LDD Review (dLDD Stewards Teams);Discipline LDD Freeze
B16 Standards Document Review | NASA-PDS/system-i-n-t | 2025-10-17 | 2025-11-27 | 41 | 378 | Standards Document Review | Review Standards Reference Document Updates;Complete Doc Updates Per Review Comments
B16 System Integration & Test | NASA-PDS/system-i-n-t | 2025-10-17 | 2025-11-27 | 41 | 378 | System Integration & Test | Perform System Testing;Generate Test Report;Update EN Node webpage with Test Report
B16 Information Model I&T | NASA-PDS/system-i-n-t | 2025-10-27 | 2025-11-06 | 10 | 399 | Information Model I&T
B16 Delivery & Deployment Review (DDR) | NASA-PDS/system-i-n-t | 2025-11-07 | 2025-12-18 | 41 | 357 | Delivery & Deployment Review (DDR) | Generate and Release Final Release Description Document (RDD);Generate & Submit DDR Presentation;Release Test Report;DDR - TBD date
B16 Deployment and Release | NASA-PDS/system-i-n-t | 2025-11-28 | 2025-12-18 | 20 | 357 | Deployment and Release | Deployment of Test Environment; Deployment of Production Environment - https://docs.google.com/spreadsheets/d/1f1zK9hdR3RWQP9PiR80EMFQ3xDqca1tK2a7oqSCKuHE/edit?usp=sharing; Webpage Updated - documents , discipline LDDs, TBD mission LDDs;Release announcement to public
0
0
0
0
Formulas:
Length (days) = DAYS([End Date],[Start Date])
End Date - Days from Release = DAYS('Release Date'!$B1,[End Date])